## The Lao Extension for Agriculture Project (LEAP)

SUMMATIVE EVALUATION REPORT

NAFES/SDC/Helvetas.

19 February 2007

FINAL REPORT

Table of Contents

An overview of the project	1

Purpose and Methodology of the evaluation:	1

Summary of Production Extension in Xaythany District/Vientiane Capital	2

Summary of Production Extension in Hadsayfong District/Vientiane Capital	4

Summary of Production Extension in Pakngeum District/Vientiane Capital	6

Summary of Production Extension in Thapabath District/Borikhamxay Province	7

Summary of Production Extension in Sayaboury District /Sayaboury province	9

Summary of Production Extension in Khoun District/ Xiengkhuang province	11

Summary of Production Extension in Thoulakhom District/Vientiane Province	13

Summary of Production Extension in Sebangfai District/Khammouane Province	15

Summary of Production Extension in Phalanxay District/Savannakhet Province	17

Summary of Production Extension in Saysetha District/Attapeu Province	18

Summary of Production Extension in Thataeng District/Sekong Province	19

Summary of Production Extension in Toumlan District/Saravane Province (From Student Book)	21

Summary of Production Extension in Nambak District/Luangphabang Province (From Student Book)	23

Summary of Production Extension in Khoun  District/Xiengkhouang Province (From Student Book)	25

Summary of Production Extension in Pakngeum  District/Vientiane Capital (From Student Book)	27

Summary of Analysis:	29

| Abbreviations |  |
| --- | --- |
| CETDU | Central Extension and Training Development Unit |
| DAFO | District Agriculture and Forestry Office |
| DEW | District Extension Worker |
| GM | Gross Margin |
| SDC | Swiss Agency for Development and Cooperation |
| ha | Hectare |
| HH | Household |
| ISU | Information Sharing Unit |
| M&E | Monitoring and Evaluation |
| LEAP | Laos Extension for Agriculture Project |
| t | Ton |
| Kip | Lao Currency |

## An overview of the project

The Laos Extension for Agriculture Project ( LEAP)  is a technical cooperation project of the Lao and Swiss Government.  LEAP is funded by the Swiss Agency for Development and Cooperation (SDC) and implemented jointly by NAFES and Helvetas.  Within NAFES, LEAP is directly supporting the work of the Central Extension and Training Development (CETDU) and – more recently- the Information Sharing Unit (ISU).  Phase I of LEAP started in November 2001 and ended in December 2004. During this period new extension approach was tested in three provinces.  Phase II, starting in January 2005 to December 2006 assisted the expansion of the approach to the entire country (18 provinces). The project goal is to support the development of a decentralized, participatory, pluralistic and sustainable agricultural extension system that reaches male and female farmers equally.

## Purpose and Methodology of the evaluation:

The purpose of evaluation is to see the outputs and impacts of the project implementation of phase II in order to draw lessons for the future planning. The evaluation report is prepared according to the TOR identified by LEAP/NAFES. Documentation used for the assignment (4 student studies and 11 district monitoring reports of the production extension in … provinces. This evaluation consists of three main parts: (1) Purpose and Methodology (2) Findings of the changes in production extension of 15 districts (3) detailed analysis of 15 districts as annexes. The analysis is mainly based on the available secondary data screened from the above-mentioned 11 monitoring reports and 4 sets of students’ thesis. The evaluation team consists of three members: one national lead consultant, one technical consultant and one assistant. The team has produced data analysis matrices to disaggregate the data. All relevant data were entered into the matrices by districts within the scope of concerned provinces focusing on Before and After.

Once all available data were entered into the matrices, calculation was made to identify the changes after the LEAP support. Then, the total sum of each data was averaged out to answer the following four questions and provide lively comments and observations on the analyzed data under the two production groups: Rice Production Group, Chicken Production Group and Pig Production Group:

- What changes have taken place in production?

- What changes have taken place in food availability?

- What changes have taken place in Income?

- What changes have taken place in Gross Margin?

The report will highlight the summary of changes in above four areas of each district. Where adequate data available, an analysis will be made to identify the change rate and impact of the extension activities supported by LEAP. Each section of the report will follow with observations and comments if the data allow us to do so. The report will also provide a brief summary of findings, comments and possible recommendations based on the analysis. The spreadsheets containing all concerned data by district will be put as an annex to this report.

## Summary of Production Extension in Xaythany District/Vientiane Capital

Production Analysis:

- Rice Production Group:

- Changes in Production: The table showed that the rice production and yield per hectar before and after for just only one vaillage: Ban Nathae. This allows us to analyze and compare the change of the rice production after the extension training activities supported by LEAP. From the figure, it was noted that the change rate for the rice production was 5 percent from 77.30 tones to 81.14 tones of this village group. Similarly, the yield per hectar has been increased by 5 percent from 3.07 tones to 3.22 tones per hectar.

- Changes in Income: After harvest, the members had the rice suplus to sell about 59.8 tons before and 63.2 tone after extension. This volume has been increased by 6 percent. One family (one member) has benefit about 10 million kips after extension.

- Changes in Gross Margin: The table shows that the amount of gross profit from rice production of Nathea group has been increased by 19 % from about 31 million kips to about 37 million kips. However, the production cost (Input and Labour Cost) has been decreased by 8 percent due to the selected farmer could reduce their working days during the rice cultivation on wet season.

- Changes in Food Availability: There is a significant of rice suplus that leads to ensure the rice security of selected farmers. According to World Food Program’s standard: one person consumed 500g/person/day of uncooked sticky rice or about 350 kg of paddy sticky rice per year, this benefit group was not affected by rice deficit situation and has more the rice to sell after extension support.

- Chicken Production Group:

- Changes in Production: The table shows that the chicken production in these three villages has increased by an average rate of 248 percent, from 13 to 47 heads per household (remaining number).  The highest increasing rate is found in Veunthone village that represent 371 percent. The main reason for the big jump was that the farmers were trained and used new technique to raise chicken and use vaccination and mortality rate is lower than was about 3 percent.

- Changes in Income:

Present table shows that the income from chicken production (chicken sold) after training of the district (3 groups) represent in total of 23,520,000 kips and equal in average of 7,840,000 kips per village (444,000 kips per household/member). The highest number of chicken sold is found in the group of Duangboudee village that represent by value of 15,440,000 kips and about 66 percent of total sale.  This income level has been increased by 253 percent, compared to last term (before extension support).

- Changes in Gross Margin:

The calculation of gross margin is based on input/labour cost and gross of sale during the monitoring term of chicken production. The input and labor cost in overall had been increased by 248 percent from 12,000 kips to 440,000 kips per household. This increase translated that the farmers had more the time to take care their chicken especially for the women. The profit rate has also increased due to volume of chicken production was high quantity and mostly of farmers have received new technique from training participation.

.

- Changes in Food Availability:

According to data available and indicators shown in table, the food availability has been calculated based on number of chicken consumed during monitoring term. After training, the total of chicken consumed in the 3 groups/three villages represent of 289 heads and in average of 16 heads per household.

Comments and Observations: - Data source: Village Monitoring Reports and a telephone conversation with Mr. Thongsouk, DEW- Coordinator, Saythany District, Vientiane Capital, date: 23/1/07 - Reliability: There are three villages: one village of rice production (according to data set available from district) and three villages of chicken production groups. - Variations: It seems that the chicken production of extension was greater due to larger number of chickens produced. Ban Douangbutdee had better results than others in chicken production. - Assessment: In overall, the rice production has been increased also with the chicken production. There was an obvious impact on livelihoods because villagers produced more chickens for consumption and sale and can generate their family’s income, especially for the women. Comments: - Data collection from household and village level is essential for good monitoring and evaluation - Monitoring and reporting format should be developed and adaptable to each activity - Income and gross margin should be shown by comparong with other sources and related indicator. - Additional reason of change should be given during report writing

## Summary of Production Extension in Hadsayfong District/Vientiane Capital

Production Analysis:

1. Rice Production Group:

- Changes in Production: The table summarized the volume of rice production before and after extension training of the three villages and showed that the total quantity of rice production has increased slightly by 20% from 99.16 tones (before) to 125.37 tones (after). The yield of rice production has also increased by 25% in an average from 3.48 tones (before) to 4.36 tones per hectare per village. The change, though small, demonstrates that the impact of the LEAP project implementation was somewhat positive.

- Changes in Income: Given the high productivity as a result of the extension training, the members of group had a surplus of rice for sale to generate income for their families. According to the available data analyzed, the amount of rice sold could generate totality of more than 82 million kips for the three villages. If it was averaged out, each household had a share of 2.8 million kips. Among the three villages, Ban Nalong came out to be the highest of the rice sale, which generated almost total 32 million kips or approximately 3.2 million kips per household.

- Changes in Gross Margin: The total cost of inputs/labor has been increased by an average of 26 percent, from 3.4 million kips to 4.3 million kips per household. This increase is due to price of some inputs was higher than was (fertilizer price and labor cost). Similarly, the profit rate was also increased by an average of 26 percent from 2 million kips before to 2.6 million kips per household after extension.

- Changes in Food Availability: The table showed the total amount of rice sold before extension has been increased by 33 percent. According to World Food Programm’s standard, these three village groups had the rice surplus to sell or exchange about 4.04 tones per household after extension and the rice sufficiency rate represent 147 percent.

2. Chicken Production Group:

- Changes in Production: The table in the annex showed the data on chicken production groups in the three villages, which has increased by 47% in total from 431 (before) to 634 heads (after) and has increased from 15 to 22 heads per household. While the highest increasing rate was found in Simmano Neua village at 108%, the lowest rate was in Nalong village at 26%. The main reason for the lowest in Nalong village was the low number of chickens produced and rather high chicken mortality rate.

- Changes in Income: The existing data from the table showed that the amount of income generated from the sale of chickens after the arrival of the extension activities was 4,340,000 kips in total for three villages and has increased by 55 percent, compared to the was before extension. An average per household was 149,655 kips. Among the three villages, Simmano Neua village had the highest income of 2,200,000 kips.

- Changes in Gross Margin: The total cost for rice production of  one household member has been changed by 28 percent from 127,000 kips to 162,000 kips. The average was about 11,250 kips per head. The profit from selling the total chickens was also increased by 43 percent from about 7,625,000 to 10,886,000 kips in total of these three villages.

- Changes in Food Availability: According to the available data from the matrix, the total chickens consumed after the extension activities were only 180 heads for the three villages, which could be averaged out at 60 heads per village and at 6 heads per household. From those indicators we can conclude that the food availability of .these villages has been changed in positive way.

Comments and Observations: - Data source: Village Monitoring Reports and a telephone conversation with Mr. Phouvanh Keonakhone, LEAP Project Coordinator, Hafsayfong District Office, Vientiane Capital. - Reliability: Three villages of Hadsayfong District consisting of 29 household members were included in the table. There was data missing on information before the extension activities supported by LEAP, which in many cased made it impossible to identify the change rate - Variations: The results varied greatly from one area to another. Where baseline data were available it was possible to conclude that there was positive impact of the extension for poorer households or women and the change rate was very close in among three villages. - Assessment: The results have shown some changes and improvement made to production of rice and chickens after the extension activities supported by LEAP. There were mostly changed in positive way, particularly the rice production could ensure the rice security and generate their household income. - Other comments: - Baseline data is essential for analyzing and evaluating the change of production status. - Standardized Monitoring Forms and reporting procedures for each activity should be developed. - The sufficient reasons of changes should be given during the report writing

## Summary of Production Extension in Pakngeum District/Vientiane Capital

Production Analysis:

1. Rice Production Group:

There is not monitoring data set of rice production in Pakngeum district, so it’s difficult to conclude that the situation of this commodity was changed in positive or negative result after extension support.

2. Chicken Production Group:

- Changes in Production: The spreadsheet shows that the number of chickens produced in the three villages has increased significantly by 372 percent or from 350 to 1,651 heads in total or from of 15 to 69 heads per household. After training, the farmers received new techniques to raise their chickens. The highlight here is found in Donehai village that the increase rate represents 1000 percent.

- Changes in Income:  The detail of the changes in income generated from chicken production was shown in the annex. In general, the number of chickens sold after the extension training activities supported by LEAP has increased by 193 percent with small volume of 100,000 kips(before) and 294,000 kips(after) per household.

- Changes in Gross Margin: According to the result of calculation in the table, the cost of inputs and labour represents 440,000 kips per household and covered about 23 percent of total revenue while the gross profit is about 77 percent. The gross profit has been increased more rapid than was due to generation techniques supported by extension activities.

- Changes in Food Availability: The total number of chickens consumed represented 165 before and 250 heads after. After extension, the number covered 37 percent of total number of chicken produced and one household could consume their chickens 10 heads.

Observations and Comments: Data source: Village Monitoring Reports, Mr. Kongma, Project Coordinator, Pakngeum district, Vientiane capital, date: Reliability: There are 3 villages and 24 households included in the study. There was data missing for rice and pig production groups enable us to analyze and compare the data before and after the extension training. Gross Margin calculation was quiet complicated and based on estimated data. Variations: The range of results was quite high for the chicken production which allowed for comments to be made about the impact of the extension. Significant increase was for the two villages: Donhay (1,000%) and Nabong (646%). Comments: - Monitoring forms for each activity should be developed based on standardized format and adjustable to actual circumstances. - Additional reasons of change should be given during the report writing

## Summary of Production Extension in Thapabath District/Borikhamxay Province

Production Analysis:

1. Rice Production Group:

1. Changes in Production:

There only one village group who produce the rice and received the technical support from the LEAP project namely Gnoy Hai. The total of rice production of village after extension has been increased by an average of 15 percent from 33.7 before to 38.7 tons. The yield ton per hectare in average has also increased by 54 percent from 1.9 to 3 tons per hectare. From this indicator translate that the extension support from the project has positive result

2. Chicken Production Group:

- Changes in Production:

The chicken production supported by LEAP project (Phase II) is found in five villages in Thaphabath district with the volume of total production after extension about 771 heads. The percentage of increase is 73 percent increased from about 11 to 19 heads per household member. This positive change is translated that the project support of extension for small raising produced a positive impact. However, there is one village that we found the number of chicken production is negative due to the number of death was quiet high (18 percent of total chickens produced).

- Changes in Income:

The present table shows that the amount of chicken sold after attending represent about 3.4 million kips in these five villages. Comparing to last year before extension support has increased by 73 percent. The higher rate is found in Thaphonsan village group that the percentage of increase represented 468 percent. However, the amount of chicken production sold was still depended on the chicken price in each period.

- Changes in Gross Margin:

The total cost of chicken production distributed by household represent about 396,000 kips per household member. This total cost included the inputs and labour cost represented about 33 percent of total revenue. The profit that the farmer earned from chicken selling after extension was about 796,000 kip per household (67 percent of total revenue). This calculation based on data obtained from district and could not be compared to the rate before extension.

- Changes in Food Availability:

According to indicators shown in table, the total of chicken consumed is 5 heads per household after extension training and has increased by 78 percent, compared to last year before.

Observations: - Data source: Monitoring data set from Mr. Kapkeo, LEAP Provincial Project Coordinator, Borikhamxay Province, dated….. - Reliability: There are nine villages and 78 households consisting in the district data set (1 of rice extension, 5 of chicken production, 3 of large livestock and 1 of fruit production). Because, there was not enough data available for large livestock and fruit production, so it’s difficult to conclude that the result is positive or negative - Variations: From indicators and analysis above, the rice production as well as chicken production both have a positive impact on livelihood and really contributed to generate family income of beneficiaries especially for the women who are closely responsible for these activities. - Other comments: - Available data from village and household level is essential for analyzing and evaluating the change of production status. - Monitoring system and reporting procedure should be set up according to each activity and responsible level for making decision. - Standard Monitoring Forms could be adaptable and easy for monitoring and evaluation aspect.

## Summary of Production Extension in Sayaboury District /Sayaboury province

Production Analysis:

1. Rice Production Group:

- Changes in Production:

The rice production of the farmers after extension training represented in total 86.2 tons and in average of 3.89 tons per household. Similarly, the yield could reach to 3.89 tons per hectare. This production level could not be compared to previous year before extension due to lack of baseline data, so it’s difficult to conclude that the result of extension for this commodity.

2. Changes in Income:

In fact, analysis of the change in income of the beneficiaries should be taken by comparing with income rate before and with other sources of incomes that the selected household members earned in the year or during monitoring term. Here, the income change and gross margin rate could not summarize due to lack of baseline data, so it’s difficult to conclude about the result of project.

- Chicken Production Group:

- Changes in Production:

The production change is evaluated base on indicators in the table in the term of before and after extension training. Before extension, one household owned chickens about 18 heads in average per household and after extension, the chicken ownership became 34 heats per household and has increased by an average of 89%. This increase demonstrates that the result of extension is positive.

- Changes in Income:

The income from chicken selling is once source of household incomes. However, it’s usually evaluated by comparing with other sources such as from large animal, vegetable, wage, rice production, etc… From the table here, the chicken sold has increased by 90 percent from 83,000 to 158,000 kips per household.

- Changes in Gross Margin:

The calculation of gross margin is made based on total of inputs cost and labor cost. According to the cost calculation of the District Extension Monitoring Team, we found that the input and labor cost have been increased by 81 percent due to the farmers use more money for chicken shed building, wile the percentage of change in profit represented 83 percent. The objectives of sale are mostly for buying new clothes and daily spenditure for their children go to school.

- Changes in Food Availability:

The volume of chicken consumed per household member represent 11 heads after training and has been increased by an average of 32 percent and equal 36 percent of total chicken produced. Mostly, the chickens were consumed during spiritual ceremonies and coming time of visitors to the house.

Comments and Observations: - Data source: Data obtained from the village monitoring reports from Sayaboury DAFO, Sayaboury province and also from a telephone conversation with the district office for additional data. - Reliability: There are 11 villages and 110 households are included in the monitoring data set. Data missing is one critical point for doing analysis - Variations: Basically, monitoring forms should be developed and adaptable with situation and useful for analysis, especially the translation of indicators of each category. Some times, the value and cost were estimated by the team leads to produce an unfair report. - Assessment: In overall, the production level of two components (rice and chicken production) has increased and created many rice and chicken surplus for sale in among household members in the district. This change translates that the extension activities have a positive impact on livelihood and could ensure the rice security in the village that benefit from the project. However, the rice production and chicken rising still face on the risks by nature, lack of fund for buying new technology and labor forces. Monitoring skill of the LEAP staffs or stakeholders from central to village level is one factor to stimulate implementers of the Leap’s activities and can reach to positive result. - Other comments: - Available data from village and household level is essential for analyzing and evaluating the change of production status. - Monitoring system and reporting procedure should be set up according to each activity and responsible level for making decision. - Standard Monitoring Forms could be adaptable and easy for monitoring and evaluation aspect.

## Summary of Production Extension in Khoun District/ Xiengkhuang province

Production Analysis:

1. Rice Production Group:

Data from the district data set could not summary in the table and analyzed in detail, so it’s still difficult to conclude that the impact of the extension support is positive.

2. Chicken Production Group:

- Changes in Production: The table shows that the chicken production for 8 villages has increased by an average of 136 percent from 18 to 42 heads per household (after sale and household consumption). The highest rate is found in Nahone village that represent 489 percent of increase from 99 heads (before) to 583 head (after). The village with the lowest per household ownership is found in Nongpheu village that represented only 10 heads after extension training activities supported by LEAP.

- Changes in Income: The amount of chicken sold has been increased by an average of 177 percent from 46,000 to 128,000 kips per household. The significant amount of chicken sold is found in Pieng village that the total number of the chicken sold represented about 2,540,000 kips. From this positive change translated that the result of chicken extension project has positive impact on family income generation of target groups

- Changes in Gross Margin: The calculation of gross margin is made based on total cost of inputs and labor calculated by DAFO extension specialist after participation in extension training, The input and labour cost were calculated by an average of all household members and have been changed from 235,000 to 555,000 kips per household. However, the gross profit of the term after extension represented 1.575,000 kips and has increased by 136 percent. From these indicators, the chicken production in 8 villages has changed in positive result.

- Changes in Food Availability: According to the indicators shown in table, the number of chicken consumed has been increased by an average of 93 percent from total of 383 to 740 heads and in average of 5.from 5.17 to 10 heads per household.

Observations and Comments: In fact, in Khoum district there are 4 components supported by the LEAP Project for household income generating. Here, we received only information on chicken production. - Data source: Student Thesis, village monitoring reports and a telephone conversation with Mr. Phouvanh Keonakhone, Project Coordinator, Hadsayfong, Vientiane capital, date: - Reliability: There are 8 villages (chicken production group) with 74 households but only four villages involved in rice production under study. Data missing was significant, information is complicated. There was no calculation of an increased rate. The data collection and consolidation were incomplete. - Variations: An average of results showed strong increase for chicken production for eight villages, of which Ban Nahon was the highest. This showed greater impact of the extension activities. Among 8 villages, 3-4 villages had better results. - Assessment: The results showed the improvement of chicken production, which had quite great impact on people’s living: more food and additional income. Since there was inadequate data on rice and pig production, it was not possible to compare the impact of extension between rice and livestock farmers. - Other comments: - Available data from village and household level is essential for analyzing and evaluating the change of production status. - Monitoring system and reporting procedure should be set up according to each activity and responsible level for making decision. - Standard Monitoring Forms could be adaptable and easy for monitoring and evaluation aspect. - The reasons of change should be reported on the reporting form

## Summary of Production Extension in Thoulakhom District/Vientiane Province

Production Analysis:

1. Rice Production Group:

- Changes in Production: The average rice production has increased by16 percent from 5.73 (before) to 6.64 tones per HH (after). The averaged yield has slightly increased by 14 percent from 0.41 to 0.46 tones per hectare. Only Ban Nakang had negative change in rice yield per ha. The highest increase rate is found in Phatao village (at 26%) compared to the years before extension. The indictors showed positive change on rice production under LEAP.

- Change in Income: An averaged income generated from rice sale was slightly increased by 15 percent from 6,355,164 kip (before) to 7,335,224 kip (after) per HH. Ban Phathao and Ban Nakang had negative income as the data indicated. However, we assumed that there was some positive impact on imcome.

- Changes in Gross Margin: The table showed an increase of cost of inputs/labour for rice production by 17 percent from 5,313,146 kip (before) to 6,221,229 kip per HH (after). The profit margin was also increased by only 14 percent from 3,847,451 kip (before) to 4,403,010 kip per HH (after). There were two villages had negative profit margin: Ban Nakang and Ban Natao (-2% and -22%). We interpreted that there was some positive change from LEAP.

- Changes in Food Availability: The data on consumption of rice showed an increase by 18 percent from 1.49 tones to 1.75 tones per HH. Among the 8 villages, Ban Phonthong and Ban Nakeo had negative change, thus we assumed that these villages may not provide accurate data.

2. Chicken Production Group:

- Changes in Production: The table shows that the chicken production in the nine villages has increased by an average rate of 57 percent, from 2303 to 3617 heads in total and from 29.91 to 46.97 heads per household.  The highest increasing rate is found in Vathath village at 141 percent, from 46 to 80 heads per household.

- Changes in Income: There was an increase of income generated from sale of chicken by 20 percent from 357,247 kip to 428,494 kip per HH (after). We anticipated some positive change from support by LEAP in chicken production.There were two villages that had negative change on income: Ban Vathat (-62%), Ban Nakeo (-3%) and Ban Phonkham (-71%). Other two villages had the highest rate of change: Ban Phonthong (272%) and Ban Natao (137%).

- Changes in Gross Margin: The total cost of chicken production including the cost of inputs/labour per HH was increased by 21 percent from 341,714 kip (before) to 413,278 kips per household member. The profit margin was significantly increased by 99 percent from 1,034,096 kip to 2,072,565 kip after the extension. When compared to the rate before extension, there was positive change.

- Changes in Food Availability: According to indicators shown in table, the averaged number of chicken consumed was slightly increased from 6 heads to 7 heads per household. We assumed that household members did not consume chicken too much but sold them to get more income.

Observations and Comments: - Data source: Monitoring data set from Thoulakhom DAFO, Vientiane province, LEAP Project Coordinator. - Reliability: Nine villages of Thoulakhom District consisting of two groups (rice production and chicken production group) and in total of 144 household members were included. There were sufficient data for analysis, thus we identified significant positive improvement in both groups as a result of extension activities supported by LEAP. - Variations: The results varied greatly from one area to another. Where data was adequate for analysis the change rate could be identified and vice versa. Where baseline data were missing, it was rather difficult to compare and identify the negative and positive impacts of the extension for poorer households or women. However, among these villages, change rate was very close. - Assessment: The results have shown some changes and improvement made to production of rice and chickens after the extension activities supported by LEAP. There was data missing for pig production. In some parts where data were sufficient, the results showed the positive impact on livelihoods such as increase in income and food availability. - Other comments: - Starting date and monitoring date should be noted in Monitoring Reports - Income rate should be compared to other baseline income: large livestock, vegetables, NTFPs, wages, trade, rice production and others. In most parts, data on Pig Production Groups were not at all available making it impossible to analyze and identify the impact of LEAP in the area. - Standardized Monitoring Forms for each activity should be developed.

## Summary of Production Extension in Sebangfai District/Khammouane Province

Production Analysis:

1. Rice Production Group:

- Changes in Production: The analysis showed data for only one village. Based on the calculation, the rice production has increased by 0.53% from 1.2 tones/ha to 1.84 tones/ha. per HH member. The yield per ha has also increased from 0.15 tones to 0.23 tones (0.53%) after the extension training.

- Changes in Income: There was data missing for the income generated from selling rice before. Therefore, the only data on imcome after the extension could not be compared. However, the averaged income per HH was 135,000 kip convinced us about some positive change of income generated from rice sale under LEAP.

- Changes in Gross Margin: The cost of inputs and labour before the extension training was increased by 53 percent from 1,539,000 kip to 2,337,000 kip per HH member. The averaged profit margin also increased by 57 percent from 270,000 kip to 423,000 kip peer HH member. Thus, we concluded that there was an increase of profit margin compared to costs involved. Compared these two figures, we assumed that there were some positive change after LEAP support.

- Changes in Food Availability: The data indicated no change to the number of tones of rice consumed by HH member. The number of tones of rice remained the same at 1.75 tones per HH member. Though no change was anticipated, rice was still available for consumption.

2. Chicken Production Group:

- Changes in Production: Total nine villages and 90 households raised chicken under the LEAP project. The data showed an increase by 437 percent from 13.11 heads (before) to. 70.42 heads as an average per HH member after the training. The averaged number of chicken died was reduced from 2.59 heads to 0.92 heads per HH member or about -62%. Therefore, we concluded that there was big positive change after LEAP support.

- Changes in Income: There was a significant change on the number of chicken sold by farmers, about 433 percent from 3.54 heads to 18.9 heads per HH member. We concluded that the impact was very significant.

- Changes in Gross Margin: The cost of inputs/labour for chicken production  indicated  greater positive change which were increased at an average of 91 percent  from 253,767 kip (before) to 483,492 kip per HH member. The profit margin average was also increased significantly by 434 percent from 267,467 kip to 1,427,596 kip per HH member. We assumed more investments costs but highly positive profit gained from chicken production. This was a clear indicator.

- Changes in Food Availability: The averaged number of chicken consumed was increased by 413 percent from 1.57 heads to 8.07 heads per HH member after the extension training, it was anticipated that there significant positive changes in food availability after the extension.

Comments and Observations: - Data source: Mr. Choumsy Xayavong, District Project Coordinator, Sebangfay District. - Reliability: There were 10 villages, 9 villages (90 HHs) for chicken production and 1 for rice production included in the data set. Some data before the extension were missing. There was no data for pig production group so we assumed that they did not involve in pig production activities. - Variations: The range of results showed greater change in chicken production and we could compare the production status before and after the LEAP’s intervention. Yes, data from some villages allow rooms for comments on the impacts of extension, though there was insufficient data, some villages have better results than others because where data are sufficient, the results were very positive. - Assessment: In principle, the changes in gross margin should be calculated based on inputs and outputs. Since majority of data before the intervention are missing, the results did not completely reflect the impact of the extension. However, some areas where data are sufficient, the results show the positive changes in production of rice and yield by ha, increase in income and larger gross margin of profit as a result of the increase of number of chicken. The impact of extension for rice and livestock farmers varied greatly depending on needs of local communities.

## Summary of Production Extension in Phalanxay District/Savannakhet Province

Production Analysis:

2. Chicken Production Group:

- Changes in Production: The data showed an increasing change in total chickens produced from 716 heads (before) to 2,377 heads (after) in 10 villages (100 HHs) representing the change rate of 232 percent in total and an average per HH.  An averaged number of chickens increased the extension training was 23.7.7 heads per HH or by 232 percent as compared to 7.16 heads per HH before the extension. The greater change was found in 4 villages (Ban Oudomxay: 606%, ban Sangsaeng: 434%, Ban Phalanneua: 275% and Ban Laoluang: 270%).

- Changes in Food Availability: Data on food availability, especially the number of chickens sold before and after the extension were missing. Only data on number of chickens consumed after the extension at an average of 4.95 heads per HH. The total chickens produced after the extension by 10 villages was 2,377 heads, with an average of 23.77 heads per HH. Among the 10 villages, Ban Xangsaeng, Ban Phalanneua, Ban Laoluang and Ban Oudomxay showed greater number of chickens after the extension than others, 459, 442, 381 and 311 heads respectively. The results showed significant change after LEAP support.

Comments and Observations: - Data source: Village Monitoring reports and telephone conversation with Mr. Bounthavy Phongsavanh, Deputy Head of District Agriculture and Forestry Office. - Reliability: There were 10 villages and 100 HHs of the chicken production groups included in the data set. There was a dada missing for rice and pig production groups which could not analyze. - Variations: The results showed the gradual change of number of chicken produced which could mean the impact of extension activities. Among 10 villages, only villages: Huayapheud and Song who showed less improvement. - Assessment: Looking at the results, we could see the positive change or impact of the extension activities on villages’ livelihoods. Again, we could not compare the difference between the impact for rice and livestock farmers due to data missing.

## Summary of Production Extension in Saysetha District/Attapeu Province

Production Analysis:

1. Rice Production Group:

- Changes in Production:  The data showed that rice production has been slightly increased from 111 tones (before) to 159 tones in total or from 2 to 3 tones per HH represents 43 percent after the LEAP support. The yield (tones) per ha has also increased from 7.09 tones/ha to 10.12 tones/ha or from 0.12 to 0.17 tones/HH representing an average of 43%. Among the villages, Ban Somkhoth has major improvement in terms of rice production in tones (88%) and yields in ha (87%).

- Changes in Income: Income generated from rice sale has increased by 100 percent from 2,180,000 Kip (before) to 136,261,000 kip (after) for all villages, except Ban Pork where there was no data. The averaged change per HH was increased by 89 percent from 1,223,390 kip (before) to 2,309,508 kip (after) indicating significant change under LEAP support. Despite the data income for Ban Pork was missing, it was very obvious that the LEAP’s intervention has very strong positive impact on the rice production and income generation for the villages included.

- Changes in Gross Margin: The change rate of the costs for inputs and labour has also increased by 29 percent from 920,797 kip to 1,187,000 kip per HH. The change rate for six villages was equally distributed. The increase indicated more activities and investment in rice production. As a result of more investment costs, profit gained was also increased by 119 ecent from 1,064,712 kip (before) to 2,334,627 kip (after). These figures showed greater improvement under LEAP project.

- Changes in Food Availability: There was also slightly change in the amount of rice consumed for three villages, except Ban pork and Thalan where there was no change. The averaged change rate per HH was 11 percent from 2 tones (before) to 3 tones (after). Though the percentage showed an increased, it was noted that the impact was not very significant.

Comments and Observations: - Data source: Data obtained from the village monitoring reports from Saysetha District Attapeu Province and also from a telephone conversation with the district office for additional data. - Reliability: There are 6 villages and 59 households included in the data set. There were some data missing for two villages. Data before and after of one village (Ban Pork) on: income from rice sale were missing. - Variations: After carefully analyzing, we noted that the income and profit were increased greatly but the amount of rice sold was only slightly changed before and after. There were data missing on pig and chicken production groups. There was no sex disaggregated data on poorer households or women who benefit from LEAP’s intervention. There was greater variation on income generated from selling rice between villages. The profit margin was quite high after LEAP support.

## Summary of Production Extension in Thataeng District/Sekong Province

Production Analysis:

1. Rice Production Group:

- Changes in Production: The matrix shows that data on rice production is available for only on village: Ban Nonsamphan. The rice production has slightly increased by 15 percent from 52.8 tones to 60.75 tones (wet season production only) in total and from 5.28 tones to 6.08 tones per HH. The change rate for yield per ha has also only increased minimally by 4 percent from 0.39 tones/ha to 0.41 tones/ha/HH. The result from one village could alos indicate improvement of rice production..

- Changes in Income: The change rate of income before and after was increased by 43 percent from 3,054,600 Kip (before) to 4,369,600 Kip (after). This data showed some improvement in income gernerated from sale of rice.

- Changes in Gross Margin: The matrix also shows that the cost of inputs/labour has also slightly changed by only 24 percent from 1,866,200 Kip (before LEAP) to 2,317,500 Kip (after LEAP’s support). Given the little improvement, the profit margin was also small. The change rate was not significantly increased, only by 22 percent from 6,053,800 Kip (before) to 7,402,500 Kip (after). Though not much, there was some impact of LEAP for this particular village if the data were right.

- Changes in Food Availability: The amount of rice consumed has very slightly changed, which increased only by 3 percent from 3.12 tones (before) to 3.20 tones (after). This indicates that not much food is available within the district if the data was reliable.

2. Chicken Production Group:

- Changes in Production: The matrix shows that all 9 villages engaged in chicken production. The analysis showed that there was significant change in number of chickens produced with an averaged increase of 53 percent from 8.61 heads (before) to 13.18 heads (after), which reflected the significant positive impact of extension training. In total, the change was from 775 heads to 1,186 heads for 9 villages. There were three villages: Vangmay, Charamkao and Palai showed greater improvement after the extension training. However, there were 4 villages such as Charammay, Korhua-Phou, Korhay-Huaylang and Chakamlit have negative figures.

- Changes in Income: The table showed that there was a significant increasingly improvement of income from the sale of chickens after the extension training under LEAP. In total and on average, the change rate has reached 76 percent from 275,444 Kip (before) to 483,889 Kip (after). The most significant improvement was seen from the three villages: Kamkock, Vangmay and Charamkao, which the change rate was 253%, 204% and 200% respectively. Again, two villages: Charammay and Korhuaphou were behind others and have negative earnings.

- Changes in Gross Margin: The total and averaged costs of inputs/labour were also increased by 24 percent from 247,569 kip to 306,778 kip after the extension. The data of total profit after the training for all 9 villages, except Charammay and  Korhuaphou, showed some improvement. The averaged change per HH was by 42 percent from 178,568 kip (before) to 252,851 kip (after). Here we saw some improvement made by LEAP project.

- Changes in Food Availability: The data showed an average of 53 percent change of the number of chicken consumed from 2.58 heads (before) to 3.96 heads after the extension training. The total number of chicken after the intervention was 356 heads with an average of 40 heads per village. The big improvement was seen from Ban Charammay, Palai, and Ban Vangmay where total number of chicken sold and consumed stood at 144, 81 and 47 heads respectively.

Comments and Observations: - Data source: Village Monitoring Reports of Thataeng District, Sekong Province and a telephone conversation with District Office. - Reliability: The total number of villages was 9 (90 households) but only one village was analyzed and compared for rice production For Chicken Production Group, there were 9 villages, which all showed significant improvement after the LEAP’s intervention compared to prior years. Available data showed different impact levels for each village and/or HH. There was a data missing on pig production groups. - Variations: The Rice Production Group (only 1 village)had shown some changes as a result of LEAP. Available data on rice for one village and chicken production for 9 villaages convinced us that LEAP has made some difference on improvement of their production. Like other districts, Thataeng had no data on how the impact of the extension has on the poorer households and/or women within the district. Obviously, the results from the matrix have shown the different results.. - Assessment: If we look from project impact angle, the results have shown significant changes and/or improvement as the impact of the extension training in the areas under study and analysis.

## Summary of Production Extension in Toumlan District/Saravane Province (From Student Book)

Production Analysis:

- Rice Production Groups:

  - Changes in Production: The table showed the negative percentage of rice production per village. The averaged change rate for yield/ha was minus by 30 percent from 1.33 to 0.93 tones/ha after. We assumed that the data were not adequate or might be possible miscalculation of data.

  - Changes in Gross Production (in Kip):, The negative averaged change of 11 percent from 1,569,567 to 1,395,900 kip for gross income generated from the production did not convince us about the impact of LEAP as it might be inaccurate calculation of data by collectors.

  - Changes in Intermediate Consumption in Kip: The data also indicated the negative change in consumption pattern of chicken after the extension programme in value per HH category. As the table showed, an average change rate was -21 percent decreased from 197,860 kip (before) to 155,833 kip per HH category.

  - Changes in Number of Working Day: The data showed an average decrease of number of working days by 12 percent from 187 to 164 days. We could interpreted in two ways: either newly introduced techniques from the extension helped farmers spend less time with high efficiency or farmers failed to work harder.

- Chicken Production Group:

- Changes in Production: The table showed the very similar positive changes of female chicken production in three villages under study. The averaged change rate was 23 percent from 16 (before) to 20 heads (after) per village.

- Changes in Gross Production (in Kip): The data demonstrated a gradual change rate of income generated from sale of chicken. An averaged changed rate per village was at 34 percent from 219,167 kip (before) to 294,667 kip (after). The data showed an encouraging change in earnings as a result of the extension activities supported by LEAP.

- Changes in Intermediate Consumption in Kip: The data also indicated the change in consumption of chicken after the extension programme translated in hard currency value per village. As the table showed, an average change rate was 8 percent from 18,433 kip (before) to 19,933 kip per village. Again, there was some positive impact of the extension activities.

- Changes in Number of Working Day: The data clearly indicated an increase of an averaged number of working days/village/year, which could be interpreted that there was a mind-shift among villagers. The data showed that an averaged number of working day/village/year has increased by 23 percent from 13 days (before) to 16 days (after). This means there was some impact of the LEAP activities.

- Changes in Added Value (AV): There was an obvious positive change in the gross income of chicken production. The averaged changed rate was 35 percent from 189,100 kip (before) to 256,167 kip per head after the extension activities.

Comments and Observations: - Data source: Student Thesis by Ms. Phimchay Chalounny and Mr. Leo Somkhamchareun: Study on impact of extension system of villages in Toumlan District, Saravane province. - Reliability: There were 7 villages involved in rice and chicken production groups. The data for rice production groups may not be accurate as they were all showed negative changes. We assumed that the data may not be realistic, which did not allow for any comments. - Variations: The results showed the gradual change of number of chicken produced, gross income, consumption patterns and value added for farmers in all three HH categories, which could mean the impact of extension activities. There was little difference between the three HH categories in terms of results. - Assessment: The results for chicken production groups showed the positive change or impact of the extension activities on villages’ livelihoods. There was difference of impact on rice and livestock farmers as there was negative change in rice production for all three HH categories. This made analysis unrealistic in terms of impact of extension for farmers.

## Summary of Production Extension in Nambak District/Luangphabang Province (From Student Book)

Production Analysis:

- Rice Production Groups:

- Changes in Production: The table showed a slightly change in percentage of yield (tones) per hectare of rice production per category of households. The averaged change rate was 17 percent from 1.79 tones/ha (before) to 2.10 tones/ha (after).

- Changes in Gross Production (in Kip): The gross income generated from rice production per village was also increased at an average of 14 percent from 2,969,167 kip (before) to 3,380,000 kip per category after the extension.

- Changes in Intermediate Consumption in Kip: There was a bit bigger change in consumption of chicken after the extension in hard currency value per village. An average change rate was 56 percent from 173,833 kip (before) to 272,000 kip category. There was some positive change, especially the poor families (156%).

- Changes in Number of Working Day: There was a reduction in number of working days for all levels of households. An averaged number of working days/village/year was reduced by 12 percent from 152 days (before) to 134 days (after).

- Changes in Added Value (AV): There was a slightly positive change in the gross income of rice production. The averaged changed rate was only 6 percent from 2,622,633 kip (before) to 2,778,800 kip per category after the extension activities.

- Pig Production Groups:

  - Changes in Production: The data showed no change for the number of pig produced stood at 1 pig per household category.

  - Changes in Gross Production (in Kip): There was 38 percent of an averaged positive change in the gross income of pig production. The averaged changed rate per category was from 603,300 kip (before) to 830,933 kip after the extension.

  - Changes in Intermediate Consumption in Kip: There was a bit bigger change in consumption of pig after the extension in hard currency value category, especially the medium HHs. An average change rate was 62 percent from 296,500 kip (before) to 481,033 kip per category. The obvious change was found in medium HHs (101%).

  - Changes in Number of Working Day: There was a slightly increase in number of working days for three categories of HHs. An averaged number of working days/category/year was increased by 16 percent from 44 days (before) to 51 days.

  - Changes in Added Value (AV): There was a significant positive change in added value from pig production. The averaged increasing rate was 42 percent from 273,467 kip (before) to 388,067 kip per category after the extension. The obvious change was found with medium HH category (82%).

- Chicken Production Groups:

- Changes in Production: The table showed unrealistic figure as the number of chicken was only 1 chicken per HH category, which was not realistic.

- Changes in Gross Production (in Kip): The data showed the significant increase gross income generated from chicken production. An averaged changed rate per category was at 56 percent from 311,733 kip (before) to 486,467 kip (after). The obvious change was found with the rich HH category (98%).

- Changes in Intermediate Consumption in Kip: There was an averaged change of 27 percent of consumption of chicken from 51,300 kip (before) to 65,400 kip after the extension. This indicated the impact of the project on livelihood.

- Changes in Number of Working Day: The data showed a slightly averaged increase of 22 percent from 11(before) to 13 working days after the extension. There might be mixed results of the use of new techniques and more time was needed to spend on the use of new techniques.

- Changes in Added Value (AV): There was an obvious significant positive change in the gross income of chicken production. The averaged changed rate was 75 percent from 217,433 kip (before) to 379,533 kip per HH category after the extension activities. The obvious change was found with rich HH category (118%).

Comments and Observations: - Data source: Student Thesis by Mr. Khamphong Phonethana and Mr. Xaysavath Panthavone: Study on impact of extension for knowledge system of 6 village pattern of LEAP in Nambak District, Luangphabang province, 2006. - Reliability: There were 6 villages involved in rice, pig and chicken production groups. The data on number of pig and chicken available from the student book did not provide accurate data to enable us to identify the changes and/or impact of LEAP on this area. - Variations: The averaged results showed significant changes of consumption patterns, earnings and added value as a result of the LEAP’s intervention. There was some variation of impact between the three HH categories: rich, medium and poor. The rich category may enjoy greater benefits on one commodity but not the others. Assessment: Obviously, the results from the analysis showed significant positive change or impact of the extension activities on villages’ livelihoods for all three HH categories. There was difference between the impact of extension for rice and livestock farmers in terms of commodities. Based on the results, we interpreted that the extension programme provided them a more efficient techniques, thus there was significant improvement in time, efforts and number of working days.

## Summary of Production Extension in Khoun  District/Xiengkhouang Province (From Student Book)

Production Analysis:

- Rice Production Groups:

- Changes in Gross Production (in Kip): The gross income generated from rice production per HH category (rich, medium and poor) was increased at an average of 34 percent from 2,096,333 kip (before) to 2,809,600 kip per category after the extension. The increase was very close among the three categories.

- Changes in Intermediate Consumption in Kip: There was a smaller change in consumption value of rice after the extension per HH category. An average change rate was only 4 percent from 490,000 kip (before) to 510,100 kip (after).The least change was found in rich HH category 9only 1%).

- Changes in Number of Working Day: There was also small increasing change in the number of working days for all three HH categories. An averaged change of the number of working days/HH category/year was 13 percent from 106 days (before) to 119 days (after). The poor HH category was the lowest (6%).

- Changes in Added Value (AV): There was a slightly increase in the value added of gross income from the rice production. The averaged changed rate was 20 percent from 1,301,333 kip (before) to 1,564,033 kip per category after the extension activities. Again the poor HH category was the lowest (7%).

- Pig Production Groups:

  - Changes in Gross Production (in Kip): There was 22 percent of an averaged positive change in the gross income of pig production. The averaged changed per category was from 2,041,333 kip (before) to 2,500,333 kip after the extension.

  - Changes in Intermediate Consumption in Kip: There was a slightly change in consumption value of pig after the extension per category. An average change rate was only 7 percent from 1,254,000 kip (before) to 1,346,333 kip per HH category. The change was very similar for each HH category.

  - Changes in Number of Working Day: There was a very little change to the number of working days for two categories of HHs (rich and poor) but no change for medium HH category. An averaged number of working days/category/year was increased by only 4 percent from 123 days (before) to 128 days. This was possibly due to the already high number of working days required by farmers.

  - Changes in Added Value (AV): There was a significant positive change in added value from pig production. The averaged increasing rate was 49 percent from 719,333 kip (before) to 1,073,133 kip per HH category after the extension. The obvious change was found with the rich and medium HH categories (62 and 58%).

- Chicken Production Groups:

  - Changes in Gross Production (in Kip): There was a small increasing change of gross income generated from chicken production. An averaged changed rate per HH category was 24 percent from 374,167 kip (before) to 462,800 kip (after). The change rate was very close among the three HH categories, except the rich (13%).

  - Changes in Intermediate Consumption in Kip: There was an averaged change of 26 percent of consumption value of chicken from 51,667 kip (before) to 65,000 kip after the extension. This indicated the little impact of the project on livelihoods.

  - Changes in Number of Working Day: The data showed a small averaged change of 19 percent from 28 (before) to 34 working days after the extension. This may be due more time needs for the newly introduced techniques from the extension for farmers.

  - Changes in Added Value (AV): There was an averaged change of 36 percent in the added value from gross income of chicken production from 288,033 kip (before) to 391,033 kip (after) for all HH categories. Again, the percentage of change was very close.

Comments and Observations: - Data source: Student Thesis by Mr. Sivay Vang and Ms. Nouphone Manivane: Study on impact of extension of farmer knowledge system of 6 villages of LEAP in Khoun District, Xiengkhouang province, 2006. - Reliability: There were 6 villages involved in rice, pig and chicken production groups. The data on number of pig and chicken available from the student book were good data, which enable us to identify the changes and/or impact of LEAP on this area. - Variations: Though there was not bigger change to production of the three commodities, the averaged results showed some promising changes of consumption patterns, earnings and added value. There was smaller difference of impact between the three HH categories: rich, medium and poor. - Assessment: The results showed some positive change so as an impact of the extension activities on villagers’ livelihoods. While some commodities provided greater benefits for the rich and medium HH categories, another commodity offered added value for the poor HH category and vice versa. As a result, there were some positive changes, thus improvement for farmers of the three HH categories.

## Summary of Production Extension in Pakngeum District/Vientiane Capital (From Student Book)

Production Analysis:

- Rice Production Groups:

- Changes in Production: The table showed a slightly change in percentage of yield (tones) per hectare of rice production per category of households. The averaged change rate was 17 percent from 1.71 tones/ha (before) to 2.00 tones/ha (after).

- Changes in Gross Production (in Kip): The gross income generated from rice production per HH category was increased significantly at an average of 166 percent from 1,017,031 kip (before) to 2,709,364 kip per HH category after the extension. The increase rate was very close among the three HH categories.

- Changes in Intermediate Consumption in Kip: There was a greater change in consumption value of chicken after the extension per HH category. An average change rate was 187 percent from 300,192 kip (before) to 861,358 kip per HH category. There was significant improvement for all three categories, particularly the rich category (235%).

- Changes in Number of Working Day: There was a reduction in number of working days for all levels of HH categories. An averaged number of working days/village/year was reduced by 5 percent from 113 days (before) to 107 days (after). This could be interpreted that farmers used new techniques and time efficiently to ensure high productivity with cost-effectiveness.

- Changes in Added Value (AV): There was a big jump for the added value from rice production. The averaged changed rate was only 126 percent from 640,143 kip (before) to 1,448,808 kip per HH category after the extension activities. Again, the change rate was very close among the three HH categories.

- Chicken Production Groups:

- Changes in Production: The table showed unrealistic figure as the number of chicken was only 1 chicken per HH category, which was not realistic.

- Changes in Gross Production (in Kip): There was a significant increase in gross income generated from chicken production. An averaged changed rate per category was at 97 percent from 309,591 kip (before) to 609,895 kip (after). The most obvious change was found with the rich and poor HH categories (148 and 121%).

- Changes in Intermediate Consumption in Kip: There was a slightly change in consumption value. The averaged change was 22 percent from 131,560 kip (before) to 160,113 kip after the extension. The bigger change was found with the rich HH category (45%).

- Changes in Number of Working Day: The data showed significant change of the number of working days with averaged increase of 68 percent from 13 (before) to 21 working days after the extension. Here again, there might be a mixed results of the use of new techniques and more time was needed to get familiar with the new system or use of new techniques.

- Changes in Added Value (AV): There was an obvious greater positive change of the added value in the gross income of chicken production. The averaged change rate was 164 percent from 152,259 kip (before) to 401,544 kip per HH category after the extension activities. The obvious significant change was found with rich and poor HH categories (253 and 225% respectively).

Comments and Observations: - Data source: Student Thesis by Mr. Souk Phomhacksa and Ms. Sonexay Souryalangsy: Study on impact Assessment of knowledge system of 3 village pattern of LEAP in Pakngeum District, Vientiane Capital, 2006. - Reliability: There were 3 villages involved in production two commodities: rice and chicken production groups. The data were sufficient for analysis, except the data on number of chicken were not realistic. - Variations: The averaged results showed significant changes of consumption patterns, earnings and added value for all two commodities of the three HH categories as a result of the LEAP’s intervention. It was noted that the number of working days for rice production were reduced due either to the need of additional days or high efficiency from the new techniques provided by LEAP. The variation of changes demonstrated different impact between the three HH categories: rich, medium and poor. - Assessment: The results from the analysis of the two commodities showed significant positive change or impact of the extension activities on villages’ livelihoods for all three HH categories. There was difference between the impact of extension for rice and livestock farmers by commodities. We interpreted that the extension programme provided them a more efficient techniques, thus there was significant improvement in time and efforts resulting in cost-effectiveness.

## Summary of Analysis

After entering the data from each district into the spreadsheet, an analysis has been made to answer the four questions stated under Purpose and Methodology Section above. Each district included in the data set consists of different number of villages. The maximum number of villages per district is 10 and minimum is 3 villages. The analysis was based on the data before and after of Rice Productions groups, Chicken Production Groups and Pig Production Groups. The change rate for each commodity within each district was calculated and the difference was identified to see the negative and positive impacts of the extension activities supported by LEAP. The following sections provides detailed findings of our analysis, followed by comments/feedback and possible recommendations.

- Findings before Extension: Based on data available from village monitoring reports, we found that a lot of baseline data on the three groups of commodities were missing. Some districts had data on one commodity but lacked the others making our analysis difficult and almost impossible in many cases. However, where some available, the results of analysis showed that rice production was lower, yield per hectare was lower. Chicken production was also dependent on traditional methods resulting in fewer healthy chicken were produced.

- Findings after Extension: After the intervention of extension activities supported by LEAP, the results of the analysis have shown greater change in terms of three commodities. These changes lead to improve livelihood as well as family income generation for the farmers who benefit from project activities, for example, rice yield per hectare in Saysetha district in saravan province has been increased by 43 percent and chicken production in Sebangfay District has increased by 633% after the KEAP support. Income generated from rice and chicken sale in other districts has also increased after the extension making gross profit of villagers increased.

- Comments: From the analysis, we found that data before and after the extension on the two commodities were significantly missing making us difficult to find the actual impact of the extension activities. Different districts used different monitoring forms and not updated to fit the district situation. Sometimes, we had to use the assumption to show some indicators in the table. Skills on data collection and analysis as well as the analytical thinking of those responsible persons might be low so required information were lost. Furthermore, the reasons/justification for the difference and change level were not cited to indicate the income level, for example. All students’ theses provided too broad data and no breakdowns by commodities and villages and could not respond four questions mentioned above.

- Possible Recommendations:

  - Monitoring format and reporting procedure should be updated and suitable for monitoring purpose,

  - Training on data collection and analysis should be provided to those who participated in the study,

  - Baseline data on these commodities should be collected and analyze during the project design,